## 1. Project Overview
Field | Your Input | Example / Guidance
PROJECT IDENTITY
Project Name | Aqarkom | RealtyFlow CRM / عقار CRM
Project Code / ID | Internal tracking code | RE-CRM-2026-001
GitHub Repository | Already set up | github.com/malhajri07/real-estate-CRM-project
Version | PRD version | v1.0
Date Created |  | 2026-03-14
Last Updated
Author(s) | PRD author(s)
Status | Draft / In Review / Approved | Draft
Reference Apps (Inspiration) | Apps used as feature references | Aqar (sa.aqar.fm) + DealApp (dealapp.sa)
EXECUTIVE SUMMARY
Problem Statement | What problem does your app solve in the Saudi market? | Saudi brokers lack a unified Arabic-first CRM to manage property sales, leases, and buyer requests across Aqar-style listings and Deal-style request-driven workflows
Product Vision | 2-3 sentence long-term vision | Become the all-in-one broker platform for the Saudi real estate market—combining Aqar's listing power with DealApp's request-matching model and a full-featured CRM/transaction engine
Elevator Pitch | One sentence | An Arabic-first real estate CRM that unifies property listings, buyer/tenant request matching, transaction management, and Ejar integration for Saudi brokers
Target Market | Geographic and demographic focus | Saudi Arabia — Riyadh, Jeddah, Dammam, Eastern Province. Brokers, agents, property managers, real estate offices
Target Launch Date
Business Model | How will the app make money? | SaaS subscription tiers + promoted listings + Aqar Plus-style premium features + transaction fees
Success KPIs | How will you measure success? | Active brokers, listings created/month, deals closed, avg. time-to-close, request-to-offer conversion rate, NPS, MRR
Competitive Advantage vs Aqar | What does your CRM do that Aqar doesn't? | Full CRM + transaction pipeline + commission tracking (Aqar is a marketplace, not a broker management tool)
Competitive Advantage vs DealApp | What does your CRM do that DealApp doesn't? | Complete listing management + document mgmt + financial tracking (DealApp focuses on request matching only)
SCOPE & CONSTRAINTS
In Scope (Phase 1 — MVP) | Core features for first release | Property listings (Aqar-style), request matching (Deal-style), CRM contacts, transaction pipeline, Arabic/English bilingual UI, map integration, Nafath auth
In Scope (Phase 2) | Growth features | Ejar integration, e-signatures, commission tracking, analytics dashboard, email/SMS campaigns, booking system
In Scope (Phase 3) | Advanced features | AI property valuation, market price insights (like Aqar's neighborhood pricing), Aqar Plus-style premium, mobile app
Out of Scope | Excluded features | Rent financing (Aqar's Ijari/Rise), construction calculator, VR tours
Budget Range
Team Composition | Current team from GitHub | TypeScript monorepo (apps/), Cursor AI-assisted development, pnpm workspace
Tech Stack (Already Chosen) | From your GitHub repo | TypeScript, Vite, React, Tailwind CSS, PostgreSQL (PLpgSQL), Docker, GCP Cloud Run, Terraform
Regulatory Requirements | Saudi-specific compliance | REGA (Real Estate General Authority) ad licensing, Nafath identity verification, Ejar rental contracts, VAT compliance, Saudi data residency
Localization | Language requirements | Arabic (primary, RTL) + English. SAR currency. Hijri + Gregorian dates. Saudi phone format (+966)
STAKEHOLDERS
Product Owner
Technical Lead
Business Sponsor
Domain Expert (Broker SME) |  | Active Saudi broker for validation
Legal / Compliance Advisor |  | REGA regulations expert

## 2. User Personas
Attribute | Persona 1: Listing Broker (وسيط عقاري) | Persona 2: Buyer/Tenant Seeker (طالب عقار - DealApp model) | Persona 3: Property Owner (مالك عقار) | Persona 4: Brokerage Manager (مدير مكتب عقاري)
Name / Title | أحمد، وسيط عقاري مرخص | سارة، باحثة عن شقة إيجار | خالد، مالك عمارة سكنية | فهد، مدير مكتب عقاري
Age Range | 28-45 | 25-40 | 40-60 | 35-55
Experience Level | 3-15 years in real estate | First-time renter/buyer | 5+ years property ownership | 10+ years managing teams
Daily Responsibilities | List properties on Aqar/DealApp, respond to requests, conduct viewings, negotiate deals | Search listings on Aqar, submit requests on DealApp, compare properties, visit showings | Monitor rent payments, review broker marketing efforts, manage multiple units | Oversee agents, track office performance, ensure REGA compliance, manage commissions
Key Goals | Close more deals faster, respond to DealApp requests quickly, build client database | Find the right property at best price, get matched with good broker, sign lease easily | Maximize occupancy, find reliable tenants, minimize vacancy, track financials | Grow brokerage revenue, improve agent productivity, track all transactions centrally
Pain Points | Scattered tools (Aqar + DealApp + WhatsApp + Excel), no unified CRM, manual commission tracking | Too many listings to filter, unreliable brokers, no transparency on pricing, complicated lease process | No visibility into broker performance, can't track which units are vacant/leased, manual rent tracking | No central system, agents use personal phones, can't see pipeline, compliance risk
Current Tools | Aqar app, DealApp, WhatsApp, Excel, phone calls | Aqar app, DealApp, Instagram, WhatsApp groups | WhatsApp with broker, bank statements, Excel | WhatsApp groups, shared Excel files, manual reports
Tech Savviness (1-5) | 4 | 3 | 2-3 | 3-4
Primary Device | Mobile (Android/iOS) + Desktop | Mobile primarily | Mobile | Desktop + Mobile
Critical Features Needed | Listing mgmt, request inbox, transaction pipeline, CRM, commission calc | Smart search, map view, request submission, broker ratings, Ejar integration | Rent roll dashboard, vacancy alerts, tenant screening, financial reports | Agent mgmt, performance dashboard, pipeline overview, compliance tracking
Language Preference | Arabic primary, English secondary | Arabic | Arabic | Arabic + English reports
Frequency of Use | Daily, 4+ hours | Weekly during search | Monthly review | Daily, 2+ hours
USER JOURNEY MAP — SELL / BUY / LEASE (Saudi Market Flow)
Stage | Sell (بيع) | Buy (شراء) | Lease (إيجار) | Request-Based (DealApp Model)
1. Lead Generation | List on Aqar, social media, office walk-ins | Search Aqar, submit DealApp request | Search Aqar rentals, submit request | Seeker submits request with specs (location, budget, type)
2. Initial Contact | Respond to inquiries via WhatsApp/app | Receive broker responses, compare offers | Contact landlord/broker, ask about availability | Broker in target neighborhood receives request notification
3. Property Matching | Share listings matching buyer criteria | Review matched properties, shortlist | Visit available units, compare | Broker sends matching property offers from their inventory
4. Viewing / Inspection | Schedule and conduct property tours | Visit properties, take notes, compare | Visit unit, check condition | Seeker reviews offers, requests viewings
5. Negotiation / Offer | Present offers, negotiate price | Submit offer, negotiate terms | Negotiate rent, lease terms, deposit | Direct negotiation between matched broker and seeker
6. Documentation | Prepare sale contract, title deed transfer | Review contract, arrange financing | Generate Ejar contract, sign | Documents handled through the platform
7. Closing / Signing | Title transfer at notary, receive commission | Sign at notary, pay, receive keys | Sign Ejar, pay deposit, get keys | Deal marked as closed, both parties rate each other
8. Post-Transaction | Follow up, request referral, update CRM | Move in, provide feedback | Pay rent monthly, maintenance requests | Broker builds reputation score for future requests

## 3. Feature Requirements
ID | Feature Name | Description / User Story | Priority (Must/Should/ Could/Won't) | Phase (1/2/3) | Size (S/M/L/XL) | Source (Aqar/Deal/ Custom) | Acceptance Criteria | Dependencies
PROPERTY MANAGEMENT — Aqar-Style Listings (إدارة العقارات)
PM-001 | Property Listing Creation (Arabic/English) | As a broker, I want to create property listings in Arabic with all details so I can market on the platform | Must | 1 | L | Aqar+Custom | Create listing with address, price, photos, description in AR/EN. All Saudi property types supported
PM-002 | Saudi Property Types Support | Support all Aqar property categories: شقق، فلل، أراضي، عمائر، دور، محلات، مكاتب، استراحات، شاليهات، مزارع، مستودعات، غرف، مخيمات | Must | 1 | M | Aqar | All 20+ Aqar property types available with type-specific fields
PM-003 | Transaction Types | Support بيع (Sale), إيجار سنوي (Annual Rent), إيجار شهري (Monthly), إيجار يومي (Daily booking), both (Sale+Rent) | Must | 1 | M | Aqar | Each listing can be tagged with transaction type, price format adapts (SAR/yearly, SAR/monthly, SAR)
PM-004 | Photo & Media Upload | Upload up to 50 photos, videos, floor plans, and virtual tour links per listing | Must | 1 | M | Aqar | WebP optimization, thumbnails auto-generated, drag-to-reorder, Matterport embed support | Cloud Storage
PM-005 | Interactive Map View (خريطة) | Display all listings on an interactive map with clustering, like Aqar's map feature | Must | 1 | L | Aqar | Map renders <2sec, clickable pins with preview cards, neighborhood boundaries, cluster at zoom levels | Google Maps API
PM-006 | Advanced Search & Smart Filters | Search by city, neighborhood (حي), price range, area (م²), rooms, property type, listing date — matching Aqar's filter system | Must | 1 | L | Aqar | All filter combos work, results <2 sec, supports Arabic neighborhood names, saved searches
PM-007 | City & Neighborhood Navigation | Browse by Saudi cities and neighborhoods with listing counts (like Aqar: الرياض 86,430) | Must | 1 | M | Aqar | All Saudi cities listed, neighborhood hierarchy, listing counts per area, SEO-friendly URLs | Saudi geo data
PM-008 | Property Status Tracking | Track: Active, Pending, Under Contract, Sold, Leased, Withdrawn, Expired | Must | 1 | S | Custom | Status changes trigger notifications, reflected across all views
PM-009 | REGA Ad Licensing Integration | Obtain real estate ad license through platform per REGA regulations | Must | 1 | L | Aqar | Listings require valid REGA ad license number, validation against REGA API | REGA API
PM-010 | Neighborhood Price Insights (إحصائيات) | Show average prices per neighborhood based on market data — like Aqar's price analytics | Should | 2 | L | Aqar | Price/m² by neighborhood, trend charts, comparison tool | Market data feed
PM-011 | Listing Promotion / Featured Ads (تمييز الإعلانات) | Allow brokers to pay to promote listings for higher visibility — Aqar's premium placement model | Should | 2 | M | Aqar | Promoted listings appear first, configurable duration, payment integration | Payment gateway
PM-012 | Property Description Search | Search within listing descriptions (Aqar Plus feature) | Could | 2 | M | Aqar | Full-text search on Arabic descriptions returns relevant results
PM-013 | Favorites on Map | View saved/favorite listings on map view | Could | 2 | S | Aqar | Favorites pins differentiated on map, quick actions from map
REQUEST MATCHING ENGINE — DealApp Model (محرك مطابقة الطلبات)
RM-001 | Property Request Submission (طلب عقاري) | As a seeker, I want to submit a property request with my requirements so brokers can find me matching properties — DealApp's core model | Must | 1 | XL | DealApp | Request form: location (city/neighborhood), type, budget range, rooms, area, timeline. Auto-notify matching brokers
RM-002 | Broker Request Inbox | As a broker, I want to see all property requests in my target neighborhoods so I can respond with matching offers | Must | 1 | L | DealApp | Filtered inbox by neighborhood, request type, budget. Real-time notifications for new requests
RM-003 | Request-to-Offer Matching | Broker responds to a request by sending one or more property offers from their inventory | Must | 1 | L | DealApp | Broker can attach listings to a request response, seeker sees all offers in one view, comparison enabled
RM-004 | Smart Auto-Matching / Alerts | Auto-match new listings with existing requests and notify seekers — Aqar's 'Property Request' feature | Should | 2 | L | Aqar+Deal | When new listing matches saved request criteria, instant push/email notification sent
RM-005 | Broker Neighborhood Specialization | Brokers declare their active neighborhoods so they receive relevant requests — DealApp's broker-neighborhood model | Must | 1 | M | DealApp | Broker profile includes active neighborhoods, requests only routed to brokers in those areas
RM-006 | Request Status Tracking | Track request lifecycle: Open → Offers Received → Under Review → In Negotiation → Closed/Expired | Must | 1 | S | DealApp | Status visible to both seeker and broker, auto-expire after configurable period
RM-007 | Broker Rating & Reviews | After a deal, both parties can rate and review each other — builds broker reputation | Should | 2 | M | DealApp | 1-5 star rating + text review, displayed on broker profile, affects request routing priority
CRM & CONTACT MANAGEMENT (إدارة العلاقات والعملاء)
CRM-001 | Contact Database (Arabic Names) | Central database supporting Arabic names, Saudi phone (+966), multiple contact types | Must | 1 | L | Custom | Contact types: Buyer, Seller, Tenant, Landlord, Vendor, Investor. Arabic name fields, Saudi ID storage
CRM-002 | Lead Capture from Multiple Sources | Capture leads from: Aqar inquiries, DealApp requests, website forms, WhatsApp, walk-ins, social media | Must | 1 | L | Custom | Lead source tracked, auto-import from Aqar/DealApp APIs if available, manual entry for WhatsApp/walk-in
CRM-003 | Lead Scoring & Qualification | Auto-score leads based on activity, budget, timeline, engagement | Should | 2 | M | Custom | Scoring rules configurable, hot/warm/cold visual indicators, auto-prioritize high-score leads
CRM-004 | Activity Timeline | Log all interactions: calls, WhatsApp messages, showings, emails, notes per contact | Must | 1 | M | Custom | Chronological activity feed, auto-log from integrated channels, manual entry for offline activities
CRM-005 | Task Management | Create/assign tasks with due dates, reminders, linked to contacts and properties | Must | 1 | M | Custom | Task list, calendar view, overdue alerts, assignment to team members
CRM-006 | Pipeline / Kanban Board | Visual drag-and-drop pipeline for leads and deals | Must | 1 | M | Custom | Kanban columns per stage, drag between stages, stage conversion metrics
CRM-007 | WhatsApp Integration | Send/receive WhatsApp messages within CRM — critical for Saudi market | Should | 2 | L | Custom | WhatsApp Business API integration, message templates, auto-log conversations to contact | WhatsApp Business API
CRM-008 | Contact Import / Export | Import from CSV, vCards, other CRMs; export in multiple formats | Must | 1 | M | Custom | Deduplication, Arabic name handling, field mapping, bulk import up to 10K
CRM-009 | Client Portal (بوابة العميل) | Secure portal for clients to view transaction status, documents, and communicate | Could | 3 | L | Custom | Client login, view property status, sign docs, message broker, progress tracker
TRANSACTION MANAGEMENT (إدارة الصفقات)
TM-001 | Sale Transaction Pipeline (بيع) | Full pipeline: Listing → Marketing → Showing → Offer → Negotiation → Contract → Title Transfer → Closing | Must | 1 | XL | Custom | Stage gates, required documents per stage, deadline tracking, all parties visible
TM-002 | Lease Transaction Pipeline (إيجار) | Pipeline: Listing → Inquiry → Viewing → Application → Credit Check → Lease Signing → Move-in | Must | 1 | XL | Custom | Lease-specific stages, tenant screening integration, Ejar contract generation
TM-003 | Purchase Transaction Pipeline (شراء) | Pipeline: Requirements → Search → Viewing → Offer → Due Diligence → Contract → Closing | Must | 1 | L | Custom | Buyer-specific milestones, financing tracking, title deed verification
TM-004 | Offer Management (العروض) | Create, send, track, and counter offers with full history | Must | 1 | L | Custom | Multiple offers per property, counter history, expiry dates, comparison view
TM-005 | Commission Calculator (حاسبة العمولة) | Calculate commission splits: broker/agent/office/referral with Saudi-standard rates | Must | 1 | M | Custom | Supports %, flat, tiered. Configurable splits. GCI tracking. VAT calculation on commission
TM-006 | Closing Checklist (قائمة الإغلاق) | Auto-generated checklist per transaction type with required Saudi documents | Should | 1 | M | Custom | Includes: title deed, REGA license, Ejar contract, power of attorney, ID copies, payment receipts
TM-007 | Timeline & Milestone Tracker | Visual timeline of key dates with Saudi business day awareness | Must | 1 | M | Custom | Gantt-style, considers Saudi weekends (Fri-Sat), Ramadan schedule adjustments, deadline alerts
TM-008 | Rent Roll Management (سجل الإيجار) | Track tenants, lease terms, rent amounts, payments for leased properties | Must | 1 | L | Custom | Multi-tenant support, renewal alerts, vacancy tracking, rent collection status
TM-009 | Earnest Money / Deposit Tracking | Track عربون (earnest money) deposits and security deposits | Should | 1 | S | Custom | Amount, date, holder, refund conditions, linked to transaction
SAUDI GOVERNMENT INTEGRATIONS (التكامل مع الأنظمة الحكومية)
GOV-001 | Ejar Integration (عقود الإيجار) | Generate and manage Ejar rental contracts directly within the app — like Aqar's Ejar feature | Must | 2 | XL | Aqar | Create Ejar contract, track status, renewal management, fully compliant with Ejar platform requirements | Ejar API
GOV-002 | Nafath Authentication (نفاذ) | Authenticate users via Saudi national SSO (Nafath) — Aqar's verified listings model | Must | 1 | L | Aqar | Login/verify via Nafath, verified badge on user profile, required for listing creation | Nafath API
GOV-003 | REGA Compliance (الهيئة العامة للعقار) | Ensure all listings have valid REGA advertising license | Must | 1 | M | Aqar | License validation, display license # on listing, compliance reporting | REGA API
GOV-004 | Real Estate Title Registry Integration | Verify property ownership via the Real Estate Register (السجل العقاري) | Could | 3 | L | Custom | Title deed verification, ownership history, geo-coordinate mapping | Real Estate Register API
GOV-005 | VAT Compliance | Handle 15% VAT on applicable real estate transactions and commissions | Must | 1 | M | Custom | Auto-calculate VAT, generate tax invoices, ZATCA e-invoicing format | ZATCA API
DOCUMENT MANAGEMENT (إدارة المستندات)
DOC-001 | Document Storage & Organization | Central document storage per transaction, contact, and property | Must | 1 | M | Custom | Folder structure, version history, access control, Arabic file names | Cloud Storage
DOC-002 | E-Signature Integration | Send documents for electronic signature | Should | 2 | L | Custom | Integration with regional e-sign provider, signing workflow, status tracking | E-sign API
DOC-003 | Arabic Template Library | Pre-built Arabic templates: sale contracts, lease agreements, power of attorney, disclosure forms | Must | 1 | L | Custom | Saudi-specific templates, auto-fill from transaction data, bilingual options
DOC-004 | Ejar Contract Generation | Auto-generate Ejar-compliant lease contracts from transaction data | Must | 2 | M | Custom | Pre-populated fields, tenant/landlord info, terms, compliant format | Ejar integration
DOC-005 | Compliance Document Checklist | Track required documents per Saudi transaction type | Must | 1 | M | Custom | Checklist: title deed, ID, REGA license, Ejar, power of attorney, NIN. Missing doc alerts
FINANCIAL & ACCOUNTING (المالية والمحاسبة)
FIN-001 | Commission Dashboard | Track earned, pending, paid commissions with VAT breakdown | Must | 1 | M | Custom | By agent, period, transaction type. GCI, net, VAT columns. SAR currency
FIN-002 | Rent Payment Tracking | Track rent payments, late fees, security deposits per unit | Must | 1 | M | Custom | Payment history, auto-reminders (SMS/WhatsApp), late fee calc, receipt generation
FIN-003 | Invoice / Receipt Generation (فواتير) | Generate Saudi tax-compliant invoices and receipts | Should | 2 | M | Custom | ZATCA e-invoicing format, QR code, Arabic/English, VAT number | ZATCA compliance
FIN-004 | Financial Reports | P&L, commission summaries, rent collection reports | Should | 2 | L | Custom | Monthly/quarterly, export to Excel, PDF. Arabic headers
FIN-005 | Rent Now Pay Later (ادفع لاحقاً) | Flexible rent payment installment options — like Aqar's Rise/Ijari partnership | Could | 3 | L | Aqar | Integration with Saudi BNPL providers (Tamara, Tabby, Rise) | BNPL API
DAILY/MONTHLY BOOKING — Aqar Reservations (الحجوزات)
BK-001 | Short-term Rental Booking | Book استراحات (rest houses), شاليهات (chalets), مزارع (farms) for daily/monthly — like Aqar's الحجوزات section | Should | 2 | L | Aqar | Calendar availability, instant booking, pricing per night/week/month, deposit handling | Payment gateway
BK-002 | Booking Calendar Management | Property owners manage availability, pricing, blackout dates | Should | 2 | M | Aqar | Drag-to-set availability, seasonal pricing, minimum stay rules
BK-003 | Booking Confirmation & Payment | End-to-end booking with payment processing | Should | 2 | M | Aqar | mada/VISA payment, confirmation email/SMS, cancellation policy enforcement | Payment gateway
COMMUNICATION (التواصل)
COM-001 | In-App Messaging | Chat between brokers, seekers, and owners within the platform | Must | 1 | M | Custom | 1:1 chat, file sharing, read receipts, notification badges
COM-002 | WhatsApp Business Integration | Deep WhatsApp integration for Saudi market (primary communication channel) | Should | 2 | L | Custom | Send listing links via WhatsApp, auto-log chats, WhatsApp click-to-chat on listings | WhatsApp Business API
COM-003 | SMS Notifications (Arabic) | Arabic SMS for key events: new request, showing confirmation, payment reminder | Must | 1 | M | Custom | Arabic SMS templates, delivery tracking, configurable triggers | SMS gateway (Unifonic/Twilio)
COM-004 | Email Integration | Send/receive emails within CRM | Should | 2 | M | Custom | Gmail/Outlook sync, auto-log to contacts, Arabic email templates | Email API
COM-005 | Push Notifications | Mobile push notifications for real-time updates | Must | 1 | S | Custom | Configurable per event type, Arabic content, FCM integration | Firebase
COM-006 | Calendar Integration | Sync showings and appointments with Google/Outlook calendar | Should | 2 | M | Custom | Bi-directional sync, showing slots, appointment booking with Saudi timezone (AST) | Calendar API
REPORTING & ANALYTICS (التقارير والتحليلات)
RPT-001 | Broker Dashboard (لوحة التحكم) | Personal KPI dashboard: pipeline, tasks, commissions, activity | Must | 1 | L | Custom | Customizable widgets, real-time data, Arabic/English toggle, mobile responsive
RPT-002 | Admin / Office Dashboard | Office-wide metrics: agent leaderboard, total revenue, pipeline health | Should | 1 | L | Custom | Multi-agent view, period comparisons, export to PDF/Excel
RPT-003 | Market Price Analytics (متوسط الأسعار) | Neighborhood average prices — like Aqar's الإحصائيات العقارية feature | Could | 3 | XL | Aqar | Price/m² per neighborhood, trend over time, comparison between areas | Market data
RPT-004 | Request Conversion Analytics | Track: requests received → offers sent → viewings → deals closed (DealApp funnel) | Should | 2 | M | DealApp | Conversion rates at each stage, by agent, by neighborhood, by property type
RPT-005 | Lead Source ROI | Which channels (Aqar, DealApp, WhatsApp, social) generate best leads | Should | 2 | M | Custom | Source attribution, cost per lead, conversion rate per source
RPT-006 | Listing Performance | Track views, inquiries, time-on-market per listing | Should | 2 | M | Custom | Per-listing analytics, recommendations for price adjustment
ADMINISTRATION & SETTINGS (الإدارة والإعدادات)
ADM-001 | User Management with Saudi Roles | RBAC: Admin (مدير), Broker (وسيط), Agent (مسوق), Assistant (مساعد), Viewer (مشاهد) | Must | 1 | M | Custom | Role-based access, REGA license verification per broker, invite via SMS
ADM-002 | Office / Team Structure | Multi-office support with team hierarchy | Must | 1 | M | Custom | Define offices, teams, assign agents, org chart, permission inheritance
ADM-003 | Commission Plan Config | Configure commission structures: splits, caps, tiers, referral fees | Must | 1 | M | Custom | Percentage, flat, tiered. Broker/office split. Cap per period. Referral tracking
ADM-004 | Bilingual System Settings | Arabic/English language toggle, RTL/LTR layout switching | Must | 1 | M | Custom | Full Arabic UI, English fallback, persisted preference, RTL CSS throughout
ADM-005 | Saudi Calendar Support | Support Hijri + Gregorian dates throughout the system | Must | 1 | S | Custom | Date picker shows both calendars, reports can use either, Ramadan awareness
ADM-006 | Data Import / Migration | Import existing data from Excel, other CRMs, Aqar export | Must | 1 | L | Custom | CSV import, field mapping, Arabic data handling, deduplication
ADM-007 | Audit Trail | Log all user actions for REGA compliance | Must | 1 | M | Custom | Timestamp, user, action, before/after values. Tamper-proof log
ADM-008 | Branding / White Label | Customize with brokerage branding | Could | 3 | M | Custom | Logo, colors, email templates, client portal branding
ADM-009 | Aqar API Integration | Sync listings to/from Aqar platform | Should | 2 | XL | Aqar | Bi-directional sync: create listing in CRM → auto-publish to Aqar, import Aqar inquiries | Aqar API access
ADM-010 | DealApp API Integration | Receive property requests from DealApp into CRM | Should | 2 | L | DealApp | Auto-import requests, send offers back, sync status | DealApp API
MOBILE APPLICATION (تطبيق الجوال)
MOB-001 | Progressive Web App (PWA) | Mobile-optimized PWA as initial mobile solution | Must | 1 | L | Custom | Offline-capable for cached data, add to homescreen, push notifications
MOB-002 | Native Mobile App (iOS + Android) | Full native mobile app — like Aqar and DealApp | Should | 3 | XL | Aqar+Deal | React Native or Flutter, full feature parity with web, App Store + Google Play
MOB-003 | Mobile Listing Creation | Create and publish listings from phone with camera integration | Must | 1 | M | Custom | Camera access for photos, GPS auto-location, quick publish
MOB-004 | Biometric Auth + Nafath | Face ID / fingerprint + Nafath SSO on mobile | Should | 2 | S | Custom | Biometric login, Nafath deep-link authentication | Nafath API

## 4. UI-UX Screens
Screen ID | Screen Name | Description / Key Elements | Access Role(s) | Inspired By / Notes | Linked Features
AUTHENTICATION & ONBOARDING
SCR-001 | Login Screen | Email/password + Nafath SSO button + OTP via Saudi mobile (+966). Arabic primary with EN toggle | All | Nafath like Aqar's verified login | ADM-001, GOV-002
SCR-002 | Registration | Role selection (Broker/Seeker/Owner), REGA license input for brokers, Nafath verification, office selection | New Users | Aqar requires Nafath for advertisers | ADM-001, GOV-002
SCR-003 | Onboarding Wizard | Profile setup, neighborhood selection (for DealApp-style requests), preferences, data import prompt | New Users | DealApp's neighborhood specialization | RM-005, ADM-006
MAIN NAVIGATION & DASHBOARD
SCR-010 | Main Dashboard (لوحة التحكم) | KPI cards (active listings, open requests, pipeline value, commission earned), task list, calendar, recent activity feed | All | Custom CRM dashboard | RPT-001
SCR-011 | Navigation Structure | Sidebar (desktop) / Bottom bar (mobile): Dashboard, Properties (عقارات), Requests (طلبات), Contacts (عملاء), Transactions (صفقات), Docs, Reports, Settings. RTL layout | All | Arabic RTL navigation | All
PROPERTY SCREENS — Aqar Style
SCR-020 | Property List (قائمة العقارات) | Card grid like Aqar: photo, price (SAR), area (م²), rooms, bathrooms, neighborhood, status badge. List/grid toggle, search bar, filters panel | Broker, Agent | Mirror Aqar listing cards | PM-005, PM-006
SCR-021 | Property Map (الخريطة) | Full-screen interactive map with property pins, cluster markers, filter sidebar, property preview cards on pin click — exactly like Aqar's map | All | Aqar's خريطة feature | PM-005
SCR-022 | Property Detail (تفاصيل العقار) | Photo gallery slider, price, specs grid (م², rooms, baths), Arabic description, location map, agent contact card, REGA license #, similar listings | All | Aqar listing detail page | PM-001
SCR-023 | Add/Edit Property (إضافة إعلان) | Multi-step form: (1) Type & transaction (2) Location picker with map (3) Details & specs (4) Photos & media (5) Price & description (6) REGA license & publish | Broker, Agent | Aqar's إضافة إعلان flow | PM-001, GOV-003
SCR-024 | Property Analytics | Per-listing: views, inquiries, days on market, price position vs neighborhood average | Broker, Agent | Aqar Plus analytics | RPT-006
REQUEST SCREENS — DealApp Style
SCR-030 | Submit Request (أضف طلب عقاري) | Form: city, neighborhood, property type, bedrooms, budget range, move-in date, special requirements. Arabic input | Seeker | DealApp's core feature | RM-001
SCR-031 | Broker Request Inbox | List of property requests in broker's neighborhoods: seeker details, requirements, budget, status, respond button | Broker, Agent | DealApp's broker interface | RM-002
SCR-032 | Request Detail & Offer Response | Request specs + list of matching properties from inventory to attach as offer. Side-by-side matching view | Broker, Agent | DealApp offer flow | RM-003
SCR-033 | Seeker Offers View | All offers received for a request: property cards, broker info, comparison table, accept/reject actions | Seeker | DealApp offer review | RM-003
CRM SCREENS
SCR-040 | Contact List (العملاء) | Search, filter by type/tag/status, Arabic name display, quick actions (call, WhatsApp, email) | Broker, Agent | Custom CRM | CRM-001
SCR-041 | Contact Detail | Profile card, activity timeline, linked properties, transactions, notes, tags. WhatsApp quick action | Broker, Agent | Custom CRM | CRM-001, CRM-004
SCR-042 | Lead Pipeline (Kanban) | Drag-and-drop Kanban: New → Contacted → Qualified → Showing → Offer → Closed/Lost | Broker, Agent | Custom CRM | CRM-006
TRANSACTION SCREENS
SCR-050 | Transaction Pipeline Board | Kanban columns per transaction type (Sale/Buy/Lease), deal cards with value, client, property, deadline | Broker, Agent | Custom CRM | TM-001/002/003
SCR-051 | Transaction Detail | Tabs: Overview, Timeline, Parties, Documents, Financial, Notes. Commission breakdown. Closing checklist | Broker, Agent | Custom CRM | TM-001
SCR-052 | Offer Comparison | Side-by-side offer comparison: price, terms, contingencies, timeline. Accept/counter/reject actions | Broker, Agent | Custom CRM | TM-004
SCR-053 | Rent Roll / Tenant Management | Table: units, tenants, rent amount, payment status, lease expiry. Vacancy highlighting. Payment history drill-down | Broker, Owner | Custom CRM | TM-008
BOOKING SCREENS — Aqar Reservations
SCR-060 | Booking Browse (الحجوزات) | Browse bookable properties (استراحات, شاليهات, مزارع) with calendar preview, daily/nightly pricing | Seeker | Aqar's الحجوزات section | BK-001
SCR-061 | Booking Calendar & Checkout | Select dates on calendar, see total price, add extras, mada/VISA payment, confirmation | Seeker | Aqar booking flow | BK-001, BK-003
DOCUMENT & FINANCIAL SCREENS
SCR-070 | Document Library | Folder tree per transaction/contact, search, upload, download, e-sign status badges | All | Custom CRM | DOC-001
SCR-071 | Commission Dashboard | Earned/pending/paid totals, by-agent breakdown, trend chart, VAT column, period filter. SAR formatting | Broker, Admin | Custom CRM | FIN-001
SCR-072 | Rent Tracker | Tenant list, payment history, overdue alerts, collection totals, receipt generation | Broker, Owner | Custom CRM | FIN-002
ADMIN SCREENS
SCR-080 | User Management | User list, role assignment (Arabic role names), REGA license verification status, Nafath verification status | Admin | Custom CRM | ADM-001
SCR-081 | Office / Team Setup | Office list, team builder, hierarchy view, neighborhood assignments per broker | Admin | Custom CRM | ADM-002
SCR-082 | System Settings (الإعدادات) | Language (AR/EN), calendar (Hijri/Gregorian), timezone, commission plans, integration APIs, branding | Admin | Custom CRM | ADM-004/005

## 5. Tech Architecture
Component | Current / Chosen (from GitHub) | Alternatives / Notes | Decision Status
PLATFORM & FRAMEWORK (from your repo)
Monorepo Structure | pnpm workspace (apps/, packages/shared/) | Turborepo for build caching | ✅ Decided
Frontend Framework | React + Vite + TypeScript | Next.js if SSR needed for SEO | ✅ Decided
CSS / Styling | Tailwind CSS (tailwind.config.ts) | shadcn/ui components for rapid UI | ✅ Decided
Backend Framework | Express/NestJS (TypeScript, apps/ directory) | Fill in your specific choice | ⬜ Confirm
Database | PostgreSQL (PLpgSQL functions in repo) | Supabase for managed PostgreSQL + auth | ✅ Decided
ORM / Query Builder | Drizzle / Prisma / raw SQL? | Fill in from your codebase | ⬜ Confirm
Build Tool | Vite (vite.config.ts) |  | ✅ Decided
Package Manager | pnpm |  | ✅ Decided
Linting / Code Quality | ESLint (eslint.config.js) | Prettier, Husky pre-commit hooks | ✅ Decided
E2E Testing | Playwright (playwright.config.ts, e2e/) |  | ✅ Decided
DEPLOYMENT & INFRASTRUCTURE (from your repo)
Cloud Provider | Google Cloud Platform (GCP) | Deploy scripts: deploy-gcp.sh, cloudbuild.yaml | ✅ Decided
Container Runtime | Docker (Dockerfile, Dockerfile.gcp, Dockerfile.dev) |  | ✅ Decided
Container Orchestration | GCP Cloud Run | docker-compose.yml for local, Cloud Run for prod | ✅ Decided
Database Hosting | GCP Cloud SQL (setup-cloud-sql.sh) |  | ✅ Decided
Infrastructure as Code | Terraform (terraform/ directory) |  | ✅ Decided
CI/CD Pipeline | Google Cloud Build (cloudbuild.yaml) |  | ✅ Decided
Process Manager | PM2 (ecosystem.config.js) | For local/dev environments | ✅ Decided
Dev Container | .devcontainer/ setup | VS Code / GitHub Codespaces ready | ✅ Decided
CDN | GCP Cloud CDN or Cloudflare | For static assets and images | ⬜ Decide
File Storage | GCP Cloud Storage (public/uploads/) | For property photos and documents | ⬜ Confirm
SAUDI-SPECIFIC INTEGRATIONS
Nafath SSO (نفاذ) |  | Saudi national digital identity — Required for verified listings | ⬜ Research API
Ejar Platform (إيجار) |  | Ministry of Housing — Rental contract management | ⬜ Research API
REGA (هيئة العقار) |  | Real Estate General Authority — Ad licensing | ⬜ Research API
ZATCA E-Invoicing (فاتورة) |  | Tax authority — For compliant invoicing with QR codes | ⬜ Research API
Real Estate Register (السجل العقاري) |  | Property title verification | ⬜ Research API
Absher / MOI |  | For tenant identity verification if needed | ⬜ Optional
THIRD-PARTY INTEGRATIONS
Maps / Geocoding | Google Maps Platform | Mapbox as alternative. Need Saudi neighborhood data | ⬜ Choose
SMS Gateway | Unifonic (Saudi) / Twilio | Unifonic preferred for Arabic SMS and Saudi numbers | ⬜ Choose
WhatsApp Business API | Meta Cloud API / 360dialog | Critical for Saudi market communication | ⬜ Choose
Payment Gateway | Moyasar / HyperPay / Tap Payments | Must support mada + VISA + Apple Pay. SAR | ⬜ Choose
E-Signature | Signatory.io (Saudi) / DocuSign | Saudi-compliant e-signatures preferred | ⬜ Choose
Email Service | SendGrid / Amazon SES | Arabic email templates support | ⬜ Choose
Push Notifications | Firebase Cloud Messaging (FCM) |  | ⬜ Setup
Analytics | Mixpanel / Google Analytics 4 |  | ⬜ Choose
Error Monitoring | Sentry |  | ⬜ Setup
Image Processing | Sharp / Cloudinary | WebP conversion, thumbnail generation | ⬜ Choose
SECURITY & COMPLIANCE
Authentication | Nafath SSO + JWT + OTP (Saudi mobile) |  | ⬜ Design
Authorization | RBAC (Role-Based Access Control) | Admin, Broker, Agent, Assistant, Viewer | ⬜ Implement
Data Encryption (at rest) | AES-256 via GCP encryption | GCP Cloud SQL default encryption | ✅ GCP default
Data Encryption (transit) | TLS 1.3 | GCP Cloud Run handles HTTPS | ✅ GCP default
Saudi Data Residency | GCP me-central1 (Dammam) region | Required for Saudi data sovereignty | ⬜ Verify region
OWASP Top 10 | Address all vulnerability categories | Regular pen testing schedule | ⬜ Audit
PII Protection | Encrypt Saudi NIN, phone, address | Separate PII storage with access logging | ⬜ Design
Backup Strategy | GCP automated daily backups | Cloud SQL automated backups, cross-region replication | ⬜ Configure
PERFORMANCE TARGETS
Expected Users (Year 1) |  | Fill: target broker count and total users | ⬜ Estimate
Peak Concurrent Users |  | Estimate peak during Saudi evening hours (8-11pm) | ⬜ Estimate
Page Load Target | < 2 seconds | On 4G connection in Saudi Arabia | Target set
API Response Target | < 500ms (P95) |  | Target set
Search Response | < 2 seconds | Property search with filters | Target set
Uptime SLA | 99.9% | During Saudi business hours (Sun-Thu) | Target set
Image Upload | < 5 seconds per photo | WebP conversion included | Target set
Map Render | < 2 seconds | With 1000+ pins | Target set

## 6. Data Model
Entity / Table | Field Name | Data Type | Req | Index | Description
TABLE: properties (العقارات)
properties | id | UUID | Y | PK | Primary key
properties | rega_ad_license | VARCHAR(30) | Y | Y | REGA advertising license number
properties | property_type | ENUM | Y | Y | شقة، فيلا، أرض، عمارة، دور، محل، مكتب، استراحة، شاليه، مزرعة، مستودع، غرفة، مخيم، أخرى
properties | transaction_type | ENUM | Y | Y | sale, annual_rent, monthly_rent, daily_rent, sale_and_rent
properties | status | ENUM | Y | Y | active, pending, under_contract, sold, leased, withdrawn, expired
properties | title_ar | VARCHAR(500) | Y | N | Arabic listing title
properties | title_en | VARCHAR(500) | N | N | English listing title
properties | description_ar | TEXT | N | FT | Arabic description (full-text indexed)
properties | description_en | TEXT | N | N | English description
properties | city | VARCHAR(100) | Y | Y | Saudi city name
properties | district | VARCHAR(100) | Y | Y | حي (neighborhood/district)
properties | street | VARCHAR(255) | N | N | Street name
properties | latitude | DECIMAL(10,8) | N | Y | Geo coordinate for map
properties | longitude | DECIMAL(11,8) | N | Y | Geo coordinate for map
properties | price | DECIMAL(15,2) | Y | Y | Price in SAR
properties | price_type | ENUM | Y | N | total, per_sqm, yearly, monthly, daily
properties | area_sqm | DECIMAL(10,2) | N | Y | Area in م²
properties | bedrooms | INT | N | Y | Number of bedrooms
properties | bathrooms | DECIMAL(3,1) | N | Y | Number of bathrooms
properties | living_rooms | INT | N | N | صالة count
properties | floor_number | INT | N | N | Which floor
properties | total_floors | INT | N | N | Building total floors
properties | year_built | INT | N | N | Hijri or Gregorian
properties | street_width_m | INT | N | N | شارع width in meters
properties | furnished | ENUM | N | N | unfurnished, partially, fully
properties | features | JSONB | N | N | مكيفات، مصعد، مواقف، حارس، etc.
properties | photos | JSONB | N | N | Array of photo URLs
properties | video_url | VARCHAR(500) | N | N | Video tour link
properties | virtual_tour_url | VARCHAR(500) | N | N | Matterport/3D tour
properties | is_promoted | BOOLEAN | Y | N | Featured/promoted listing
properties | promotion_expires | TIMESTAMP | N | N | When promotion ends
properties | listing_agent_id | UUID FK | Y | Y | FK → users
properties | owner_contact_id | UUID FK | N | Y | FK → contacts
properties | views_count | INT | Y | N | Default 0
properties | inquiries_count | INT | Y | N | Default 0
properties | listing_date | DATE | Y | Y
properties | expiration_date | DATE | N | Y
properties | created_at | TIMESTAMPTZ | Y | N
properties | updated_at | TIMESTAMPTZ | Y | N
TABLE: property_requests (طلبات عقارية — DealApp)
property_requests | id | UUID | Y | PK
property_requests | seeker_id | UUID FK | Y | Y | FK → users (the requester)
property_requests | request_type | ENUM | Y | Y | buy, rent_annual, rent_monthly, rent_daily
property_requests | property_type | ENUM | Y | Y | Same enum as properties
property_requests | city | VARCHAR(100) | Y | Y | Target city
property_requests | districts | JSONB | Y | Y | Array of target neighborhoods
property_requests | budget_min | DECIMAL(15,2) | N | Y | Min budget SAR
property_requests | budget_max | DECIMAL(15,2) | Y | Y | Max budget SAR
property_requests | bedrooms_min | INT | N | N | Minimum bedrooms
property_requests | area_min_sqm | DECIMAL(10,2) | N | N | Minimum area
property_requests | move_in_date | DATE | N | N | Desired move-in date
property_requests | additional_requirements | TEXT | N | N | Free text requirements
property_requests | status | ENUM | Y | Y | open, offers_received, in_review, in_negotiation, closed, expired
property_requests | offers_count | INT | Y | N | Number of broker offers received
property_requests | expires_at | TIMESTAMPTZ | N | Y | Auto-expire date
property_requests | created_at | TIMESTAMPTZ | Y | N
TABLE: request_offers (عروض على الطلبات)
request_offers | id | UUID | Y | PK
request_offers | request_id | UUID FK | Y | Y | FK → property_requests
request_offers | broker_id | UUID FK | Y | Y | FK → users (responding broker)
request_offers | property_id | UUID FK | Y | Y | FK → properties (offered listing)
request_offers | message | TEXT | N | N | Broker's message to seeker
request_offers | status | ENUM | Y | Y | sent, viewed, interested, rejected, accepted
request_offers | created_at | TIMESTAMPTZ | Y | N
TABLE: contacts (العملاء)
contacts | id | UUID | Y | PK
contacts | contact_type | ENUM | Y | Y | buyer, seller, tenant, landlord, vendor, investor
contacts | first_name_ar | VARCHAR(100) | Y | Y | Arabic first name
contacts | last_name_ar | VARCHAR(100) | Y | Y | Arabic last name
contacts | first_name_en | VARCHAR(100) | N | N | English first name
contacts | last_name_en | VARCHAR(100) | N | N
contacts | email | VARCHAR(255) | N | Y
contacts | phone | VARCHAR(20) | Y | Y | +966 format
contacts | whatsapp | VARCHAR(20) | N | N | May differ from phone
contacts | national_id | VARCHAR(20) | N | N | Saudi NIN (encrypted)
contacts | company | VARCHAR(255) | N | N
contacts | lead_source | ENUM | N | Y | aqar, dealapp, website, whatsapp, walkin, social, referral
contacts | lead_score | INT | N | Y | 0-100
contacts | lead_status | ENUM | N | Y | new, contacted, qualified, nurture, lost, converted
contacts | assigned_agent_id | UUID FK | N | Y | FK → users
contacts | tags | JSONB | N | N
contacts | notes | TEXT | N | N
contacts | created_at | TIMESTAMPTZ | Y | N
contacts | updated_at | TIMESTAMPTZ | Y | N
TABLE: transactions (الصفقات)
transactions | id | UUID | Y | PK
transactions | transaction_type | ENUM | Y | Y | sale, purchase, lease
transactions | status | ENUM | Y | Y | initiated, active, under_contract, pending_close, closed, cancelled
transactions | property_id | UUID FK | Y | Y | FK → properties
transactions | primary_agent_id | UUID FK | Y | Y | FK → users
transactions | client_contact_id | UUID FK | Y | Y | FK → contacts
transactions | co_agent_id | UUID FK | N | N | Other side agent/broker
transactions | list_price | DECIMAL(15,2) | N | N | Original list price SAR
transactions | final_price | DECIMAL(15,2) | N | N | Final agreed price SAR
transactions | commission_rate | DECIMAL(5,4) | N | N | Commission %
transactions | commission_amount | DECIMAL(12,2) | N | N | Total commission SAR
transactions | vat_amount | DECIMAL(10,2) | N | N | 15% VAT on commission
transactions | contract_date | DATE | N | Y
transactions | closing_date | DATE | N | Y
transactions | ejar_contract_number | VARCHAR(50) | N | N | Ejar contract reference
transactions | lease_start | DATE | N | N
transactions | lease_end | DATE | N | N
transactions | lease_monthly_rent | DECIMAL(10,2) | N | N
transactions | deposit_amount | DECIMAL(10,2) | N | N | عربون / security deposit
transactions | source_request_id | UUID FK | N | N | FK → property_requests (if from DealApp flow)
transactions | created_at | TIMESTAMPTZ | Y | N
transactions | updated_at | TIMESTAMPTZ | Y | N
TABLE: users (المستخدمين)
users | id | UUID | Y | PK
users | email | VARCHAR(255) | Y | Y
users | phone | VARCHAR(20) | Y | Y | +966
users | password_hash | VARCHAR(255) | Y | N
users | role | ENUM | Y | Y | admin, broker, agent, assistant, viewer, seeker, owner
users | nafath_verified | BOOLEAN | Y | N | Nafath SSO verification status
users | first_name_ar | VARCHAR(100) | Y | N
users | last_name_ar | VARCHAR(100) | Y | N
users | rega_license_number | VARCHAR(50) | N | Y | For brokers/agents
users | rega_license_expiry | DATE | N | N
users | brokerage_id | UUID FK | N | Y | FK → brokerages
users | team_id | UUID FK | N | Y | FK → teams
users | active_neighborhoods | JSONB | N | N | For DealApp-style request routing
users | rating_avg | DECIMAL(2,1) | N | N | Broker rating (1.0-5.0)
users | rating_count | INT | N | N | Number of ratings
users | is_active | BOOLEAN | Y | N
users | preferred_language | ENUM | Y | N | ar, en
users | created_at | TIMESTAMPTZ | Y | N
TABLE: bookings (الحجوزات — Aqar-style)
bookings | id | UUID | Y | PK
bookings | property_id | UUID FK | Y | Y | FK → properties (must be daily/monthly type)
bookings | guest_contact_id | UUID FK | Y | Y | FK → contacts
bookings | check_in | DATE | Y | Y
bookings | check_out | DATE | Y | Y
bookings | total_price | DECIMAL(10,2) | Y | N
bookings | deposit_amount | DECIMAL(10,2) | N | N
bookings | status | ENUM | Y | Y | pending, confirmed, checked_in, completed, cancelled
bookings | payment_status | ENUM | Y | N | pending, paid, refunded
bookings | cancellation_policy | TEXT | N | N
bookings | created_at | TIMESTAMPTZ | Y | N
TABLE: ADD MORE TABLES: activities, documents, commissions, showings, offers, messages, notifications, audit_log

## 7. Non-Functional Reqs
NFR ID | Category | Requirement | Priority | Target | Validation
PERFORMANCE
NFR-001 | Performance | Page load < 3 sec on Saudi 4G networks | Must | < 3 sec (P95) | Lighthouse + real device testing in KSA
NFR-002 | Performance | API responses < 500ms for standard queries | Must | < 500ms (P95) | Load testing (k6)
NFR-003 | Performance | Property search returns results < 2 seconds with filters | Must | < 2 sec | Automated tests
NFR-004 | Performance | Map renders 1000+ pins < 2 seconds | Must | < 2 sec | Map performance testing
NFR-005 | Performance | Image upload + WebP conversion < 5 sec/photo | Should | < 5 sec | Upload benchmarks
LOCALIZATION & RTL
NFR-010 | Localization | Full Arabic RTL support across all screens and components | Must | 100% RTL | Visual QA on all screens
NFR-011 | Localization | Arabic/English bilingual UI with instant toggle — no page reload | Must | Instant switch | User testing
NFR-012 | Localization | Hijri + Gregorian date display throughout | Must | Both calendars | Date format testing
NFR-013 | Localization | SAR currency formatting with Arabic numerals option | Must | ر.س formatting | Display testing
NFR-014 | Localization | Saudi phone format (+966 5XX XXX XXXX) validation | Must | Saudi format | Input validation tests
SECURITY & COMPLIANCE
NFR-020 | Security | Saudi data residency: all data hosted in GCP me-central1 (Dammam) | Must | KSA region only | Infrastructure audit
NFR-021 | Security | All data encrypted at rest (AES-256) and in transit (TLS 1.3) | Must | Full encryption | Security audit
NFR-022 | Security | OWASP Top 10 vulnerabilities addressed | Must | Pass scan | Pen testing
NFR-023 | Security | Saudi National ID (NIN) stored encrypted with access logging | Must | Encrypted PII | Data audit
NFR-024 | Security | Nafath identity verification for broker accounts | Must | Nafath verified | Integration test
NFR-025 | Security | REGA compliance for all property listings | Must | License required | Compliance check
NFR-026 | Security | ZATCA e-invoicing compliance for financial transactions | Should | ZATCA format | Invoice validation
AVAILABILITY & SCALABILITY
NFR-030 | Availability | 99.9% uptime during Saudi business hours (Sun-Thu 8am-10pm AST) | Must | 99.9% | GCP monitoring
NFR-031 | Scalability | Handle 10,000+ property listings without degradation | Must | 10K+ listings | Load testing
NFR-032 | Scalability | GCP Cloud Run auto-scaling for traffic spikes | Must | Auto-scale | Traffic simulation
NFR-033 | Reliability | RPO < 1 hour, RTO < 15 minutes | Must | RPO/RTO targets | DR drills
USABILITY & ACCESSIBILITY
NFR-040 | Usability | Mobile-first responsive design — 70%+ Saudi users on mobile | Must | All screens responsive | Device matrix testing
NFR-041 | Usability | New broker can create first listing within 5 minutes | Should | < 5 min | User testing
NFR-042 | Usability | Offline mode for cached listings and contacts (PWA) | Should | Core data offline | PWA testing
NFR-043 | Usability | Touch-friendly interface for Arabic RTL mobile use | Must | No RTL tap issues | Mobile QA

## 8. Release Plan
Phase | Milestone / Sprint | Features Included | Start | End | Dependencies / Notes
PHASE 1: MVP — Core CRM + Aqar-Style Listings + DealApp Requests
Phase 1 | Sprint 1-2: Foundation | Auth (Nafath SSO + email/OTP), user management, RBAC, Arabic RTL shell, PostgreSQL setup on GCP |  |  | GCP infrastructure, Nafath API access
Phase 1 | Sprint 3-4: Property Core | Aqar-style listing CRUD (all Saudi types), photo upload, status tracking, REGA license validation |  |  | Cloud Storage, REGA API
Phase 1 | Sprint 5-6: Search & Map | Advanced search/filters, interactive map view, city/neighborhood navigation, Arabic full-text search |  |  | Google Maps API, Saudi geo data
Phase 1 | Sprint 7-8: Request Engine | DealApp-style request submission, broker inbox, request-to-offer matching, neighborhood routing |  |  | Core of DealApp model
Phase 1 | Sprint 9-10: CRM Core | Contact database, lead capture, activity logging, task management, Kanban pipeline
Phase 1 | Sprint 11-12: Transactions | Sale/buy/lease pipelines, offer management, closing checklist, timeline tracker, rent roll |  |  | Depends on property + CRM
Phase 1 | Sprint 13-14: Docs & Comms | Document storage, Arabic templates, in-app messaging, SMS notifications, basic commission calc |  |  | SMS gateway setup
Phase 1 | Sprint 15-16: Polish & Launch | Dashboard, testing, bug fixes, performance optimization, Playwright E2E, beta launch |  |  | Beta testers (5-10 Saudi brokers)
PHASE 2: Growth — Integrations & Advanced Features
Phase 2 | Sprint 17-18: Ejar Integration | Ejar rental contract creation/management within the platform |  |  | Ejar API access
Phase 2 | Sprint 19-20: Communication | WhatsApp Business integration, email sync, calendar integration |  |  | WhatsApp Business API
Phase 2 | Sprint 21-22: Financial | Commission dashboard, rent payment tracking, invoice generation (ZATCA compliant) |  |  | ZATCA API, payment gateway
Phase 2 | Sprint 23-24: Analytics | Broker dashboard, admin dashboard, request conversion analytics, listing performance |  |  | Data accumulation from Phase 1
Phase 2 | Sprint 25-26: Automation | Auto-matching (requests ↔ listings), drip campaigns, workflow rules, broker ratings
Phase 2 | Sprint 27-28: Aqar/DealApp API | Sync listings to Aqar, import requests from DealApp, cross-platform management |  |  | Aqar API + DealApp API access
PHASE 3: Scale — Mobile, AI, Premium
Phase 3 | Sprint 29-32: Native Mobile App | React Native / Flutter app — iOS + Android — full feature parity |  |  | App Store + Google Play accounts
Phase 3 | Sprint 33-36: Market Intelligence | Neighborhood price insights (Aqar-style), AI property valuation, market trends |  |  | Market data pipeline
Phase 3 | Sprint 37-40: Premium & Booking | Aqar Plus-style premium tier, short-term booking system, rent financing (BNPL), white-label branding |  |  | BNPL provider partnership

## 9. Competitive Analysis
Feature / Capability | Aqar (sa.aqar.fm) | DealApp (dealapp.sa) | Your CRM (RealtyFlow)
CORE MODEL
Business Model | Marketplace: listings + promoted ads + Aqar Plus subscription | Request-matching: seekers post requests, brokers respond with offers | CRM + Marketplace hybrid: listing mgmt + request matching + full broker CRM
Primary User | Property seekers + advertisers (brokers/owners) | Property seekers + neighborhood brokers | Brokers (primary), seekers, property owners
Revenue Model | Promoted listings, Aqar Plus premium, Ejar services | Subscription + request fees | SaaS subscription + promoted listings + transaction fees
Market Position | #1 Saudi real estate app (12M+ downloads, 400M+ monthly searches) | Growing proptech ($2.24M raised, 100K+ requests, 20K+ agents) | New entrant — differentiate on CRM/broker management
PROPERTY LISTINGS
Property Listing Creation | ✅ Full listing with REGA license | ❌ Not primary focus | ✅ Full Aqar-style listing + CRM linking
Property Types (20+ Saudi types) | ✅ Complete (شقق, فلل, أراضي, etc.) | ✅ Basic types | ✅ All Aqar types + custom
Photo/Media Upload | ✅ Multiple photos, descriptions | ⚠️ Limited | ✅ 50 photos, video, virtual tours
Interactive Map (خريطة) | ✅ Full map with filters | ⚠️ Basic map | ✅ Full Aqar-style map
Advanced Filters | ✅ City, neighborhood, price, type, rooms, area | ⚠️ Basic filters | ✅ All Aqar filters + saved searches
Neighborhood Price Insights | ✅ Average prices per neighborhood | ❌ | ✅ Phase 2-3
Listing Promotion (تمييز) | ✅ Paid featured listings | ❌ | ✅ Phase 2
REGA Ad License Integration | ✅ Required for all listings | ⚠️ Partial | ✅ Phase 1
Aqar Plus (premium search) | ✅ Search in descriptions, map favorites, owner-only listings | ❌ | ✅ Phase 2-3
REQUEST MATCHING (DealApp Model)
Property Request Submission | ✅ Property request feature (basic) | ✅ Core feature — detailed requests | ✅ Full DealApp-style requests
Broker Request Inbox | ❌ No broker-facing request inbox | ✅ Brokers receive requests in their neighborhoods | ✅ Full inbox with matching
Request → Offer Matching | ❌ | ✅ Brokers respond with property offers | ✅ Broker sends listings as offers
Broker Neighborhood Specialization | ❌ | ✅ Brokers declare active neighborhoods | ✅ Configurable per broker
Auto-Match Alerts | ✅ Basic notification for new matching listings | ❌ | ✅ Smart matching engine
Broker Ratings | ❌ | ✅ Post-deal ratings | ✅ Phase 2
CRM & BROKER TOOLS
Contact/Lead Management | ❌ No CRM | ❌ No CRM | ✅ Full CRM with Arabic names, Saudi phone
Lead Pipeline (Kanban) | ❌ | ❌ | ✅ Drag-and-drop pipeline
Activity/Interaction Tracking | ❌ | ❌ | ✅ Full activity timeline
Task Management | ❌ | ❌ | ✅ Tasks with reminders
WhatsApp Integration | ❌ External | ❌ External | ✅ Phase 2 — deep integration
Transaction Pipeline | ❌ | ❌ | ✅ Sale/buy/lease pipelines
Commission Tracking | ❌ | ❌ | ✅ Full commission mgmt with VAT
Rent Roll / Tenant Management | ❌ | ❌ | ✅ Multi-tenant rent tracking
GOVERNMENT INTEGRATIONS
Nafath Authentication (نفاذ) | ✅ Required for advertisers | ⚠️ Unknown | ✅ Phase 1
Ejar Contract Integration (إيجار) | ✅ Full Ejar integration | ❌ | ✅ Phase 2
ZATCA E-Invoicing | ❌ | ❌ | ✅ Phase 2
Real Estate Register (السجل العقاري) | ❌ | ❌ | ✅ Phase 3
BOOKING & PAYMENTS
Short-term Booking (الحجوزات) | ✅ Chalets, rest houses, farms | ❌ | ✅ Phase 2
Rent Now Pay Later | ✅ Rise, Ijari partnerships | ❌ | ✅ Phase 3
Payment Processing | ✅ Internal | ⚠️ Limited | ✅ Phase 2 (mada, VISA)
TECHNOLOGY
Mobile App | ✅ iOS + Android (native) | ✅ iOS + Android | Phase 1: PWA, Phase 3: Native
Bilingual (AR/EN) | ✅ Arabic primary, English available | ✅ Arabic primary, English available | ✅ Full bilingual RTL/LTR
Hijri Calendar | ⚠️ Limited | ⚠️ Limited | ✅ Full Hijri + Gregorian

## 10. Risk Register
ID | Risk | Impact | Likely (H/M/L) | Impact (H/M/L) | Level | Mitigation | Owner
RSK-001 | Nafath API access delayed or restricted | Cannot verify broker identities, blocks REGA compliance | M | H | High | Apply for Nafath API early, build email/OTP fallback auth, engage SDAIA liaison
RSK-002 | Ejar API integration complexity | Cannot offer in-app Ejar contracts — key differentiator lost | M | H | High | POC spike in Sprint 1, engage Ministry of Housing developer program, manual Ejar link as fallback
RSK-003 | REGA regulation changes | Listing requirements may change, requiring app updates | M | M | Medium | Monitor REGA announcements, modular compliance layer, legal advisor on retainer
RSK-004 | Aqar/DealApp API access not available | Cannot sync listings or import requests from competitor platforms | H | M | High | Build manual import (CSV), browser extension scraper as backup, focus on organic CRM value
RSK-005 | Saudi data residency compliance | GCP me-central1 limitations or higher costs | L | H | Medium | Verify GCP Dammam region has all required services, budget for premium pricing, test early
RSK-006 | Low broker adoption | Revenue miss, product failure | M | H | High | Beta program with 10 brokers in Eastern Province, free tier, WhatsApp-based onboarding, Arabic-first UX
RSK-007 | WhatsApp Business API restrictions | Key communication channel unavailable in-app | M | M | Medium | Apply for Meta Business verification early, Unifonic as middleware, click-to-WhatsApp as fallback
RSK-008 | Arabic RTL UI bugs across browsers/devices | Poor user experience for primary language | H | M | High | RTL testing in CI pipeline, Tailwind RTL plugin, device testing matrix (Samsung, iPhone, Huawei)
RSK-009 | Payment gateway SAR/mada integration delay | Cannot process Saudi payments for bookings/promotions | M | M | Medium | Engage Moyasar/HyperPay early, bank transfer as interim, mada certification timeline tracking
RSK-010 | Competition from Aqar adding CRM features | Market leader adds broker management tools | M | H | High | Move fast on CRM differentiation, deep DealApp integration, focus on broker workflow not just marketplace
RSK-011 | Team capacity — solo/small developer team | Development takes longer than planned | H | M | High | AI-assisted development (Cursor), prioritize ruthlessly, Phase 1 MVP only, outsource non-core
RSK-012 | ZATCA e-invoicing compliance complexity | Financial features delayed or non-compliant | M | M | Medium | Use ZATCA-certified SDK, engage ZATCA sandbox early, phase 2 implementation

## 11. Glossary
English Term | Arabic Term | Definition | Context
Aqar | عقار | Saudi Arabia's #1 real estate marketplace app (sa.aqar.fm) — 12M+ downloads, 400M+ monthly searches | Reference app
DealApp | ديل | Saudi proptech app using request-matching model — seekers post requests, brokers respond with offers | Reference app
REGA | الهيئة العامة للعقار | General Authority for Real Estate — regulates real estate advertising and licensing in Saudi Arabia | Compliance
Nafath | نفاذ | Saudi National Digital Identity platform (SDAIA) — Single Sign-On for government-verified identity | Authentication
Ejar | إيجار | Ministry of Housing platform for registering and managing rental contracts digitally | Lease management
ZATCA | هيئة الزكاة والضريبة والجمارك | Zakat, Tax and Customs Authority — mandates e-invoicing format for businesses | Financial compliance
VAT | ضريبة القيمة المضافة | 15% Value Added Tax applicable to certain real estate transactions and services | Financial
NIN | رقم الهوية الوطنية | Saudi National Identification Number — 10-digit ID for citizens | Identity
Sakani | سكني | Ministry of Housing program supporting Saudi citizens with housing solutions | Government program
Title Deed | صك الملكية | Official property ownership document registered with the Real Estate Register | Documentation
mada | مدى | Saudi debit card payment network — most common payment method in KSA | Payments
SAR | ريال سعودي | Saudi Riyal — official currency | Financial
م² | متر مربع | Square meter — standard area measurement for Saudi real estate | Property specs
حي | حي | Neighborhood/district — primary location unit in Saudi real estate (e.g., حي النرجس) | Location
عربون | عربون | Earnest money / good faith deposit paid to secure a property deal | Transactions
وسيط عقاري | وسيط عقاري | Licensed real estate broker/agent in Saudi Arabia | Users
طلب عقاري | طلب عقاري | Property request — DealApp model where seekers post requirements for brokers to match | DealApp feature
إعلان عقاري | إعلان عقاري | Property advertisement/listing — requires REGA license to publish | Listings
GCI | إجمالي العمولة | Gross Commission Income — total commission before splits and fees | Financial
RTL | من اليمين إلى اليسار | Right-to-left text direction — required for Arabic UI | Technical
AST | توقيت السعودية | Arabia Standard Time (UTC+3) — Saudi Arabia timezone | Technical
PWA | تطبيق ويب تقدمي | Progressive Web App — mobile-optimized web app with offline capability | Technical